## Sheet1
NOTE: this is the agent task view shows the tasks ASSIGNED to people. In previous deliverables, the agent task view was a combination of assignments and who did what task.
Members would shift around and end up doing/helping out other people's task.

x = assigned and sufficiently contributed
x = not intially assigned, but ended up working on
x = assgined, but did not do/contribute sufficiently

This task view is fixed up and now to show intial task assignmends. More info on who actually did what, and whether they contributed sufficiently is in the other task view

note: if no date of completion is specified, assume completed sometime around the due date (day of, or few days before)

DELIVERABLE 1

	Tasks					TYPE	DUE	Status	Comments
Agents		Vivian	Dennis	Ryan	Moath	Kedar	Anwar	Alice
	Assign roles to members	x	x	x	x	x	x	x	Mandatory	26-Sep	DONE
	Finalize the role assignment document	x					Mandatory	26-Sep	DONE
	Brainstorm questions for the client	x	x	x	x	x	x	x	Mandatory	29-Sep	DONE
	Finalize the questions document	x					Mandatory	29-Sep	DONE
	Plan out tasks for DELIVERABLE 2	x	x	x	x	x	x	x	Optional	29-Sep	DONE
	Organize all the meeting minutes up to date	x					Optional		DONE

DELIVERABLE 2

	Tasks					TYPE	DUE	Status	Comments
Agents		Vivian	Dennis	Ryan	Moath	Kedar	Anwar	Alice
	Unit tests	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE	Some members did not write proper unit tests (not QT test)
	Tests cases (high level)	x	x			x			Mandatory	21-Oct	DONE: Oct 16	deliverable requirements were not clear. High level test cases were done, but TA's were looking more for low level unit tests
	Fix code for failing test cases			x		x	x	x	Mandatory	21-Oct	DONE	Assigned some members to fix code, some members did not do this
	Matrices	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE
	Document bugs	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE	Did not match up bugs to corresponding test cases because of miscommunication among members
	Document decided improvements	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE: oct 16	All members were required to brainstorm improvements and stretch goals
	Finalize code and merge		x				x		Mandatory	21-Oct	DONE
	Assess the Peach Galaxy's UI	x		x	x				Mandatory	21-Oct	DONE: oct 18
	Assess the Peach Galaxy's documentation	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE: oct 19	all members were required to help out with documentation tasks
	Assess the Peach Galaxy's code	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE: oct 19
	Finalize documents	x	x	x	x	x	x	x	Mandatory	21-Oct	DONE
	Organize all the meeting minutes up to date	x	x					Mandatory	21-Oct	DONE
					Note: for this deliverable, some members would do a task, but not contribute as much

DELIVERABLE 3 (STAGE 1)

	Tasks					TYPE	DUE	Status	Comments
Agents		Vivian	Dennis	Ryan	Moath	Kedar	Anwar	Alice
	Add line graph	x			x	x			Mandatory	31-Oct	IN PROGRESS	Originally Vivian, Moath, and kedar were set to work together for the line graph, but Moath decided that he would be okay on his own for now
	Adding session save state					x	x	Mandatory	31-Oct	IN PROGRESS
	create/update test cases and unit tests	x	x	x	x	x	x	x	Mandatory	31-Oct	unassigned	left task open to everyone, but did not have time to do it
	create/update test matrices	x	x	x	x	x	x	x	Mandatory	31-Oct	unassigned	left task open to everyone, but did not have time to do it
	add ability to modify sort order (ApplePicker Mp4, change ascneding descending)	x					STRETCH	31-Oct	DONE	NOTE: originally this was mislabelled as user selected list
	Fix export to PDF error		x					Optional	31-Oct	DONE: oct 30	fixing bugs was left open to everyone
	Fix pie chart colours		x					Optional	31-Oct	DONE: oct 30
	Add stacked bar graph	x			x	x			Mandatory	31-Oct	IN PROGRESS	see line graph comment
	deliver an exe		x					STRETCH	31-Oct	DONE	note: was not required for this deliverable
	Create a use case diagram	x	x	x		x		x	Mandatory	31-Oct	DONE: oct 31	NOTE: diagram was complete, but was forgotten in final submission
	create original class diagram					x			Mandatory	31-Oct	DONE?	NOTE: class diagram was NOT done properly
	create enhanced class diagram					x			Mandatory	31-Oct	DONE?	NOTE: class diagram was NOT done properly; unsure if the enhanced diagram was actually completed because the file was unreadable
	organize agent-view	x					Mandatory	31-Oct	DONE
	Organize task management system (Trello)	x	x		x		x		Optional	31-Oct	DONE
	Plan task allocation from Stage 1 to Stage 2	x	x	x	x	x	x	x	Mandatory	31-Oct	DONE
	Finalize code and merge	x	x				x		Mandatory	31-Oct	DONE
	Organize meeting minutes up to date	x					Mandatory	31-Oct	DONE

NOTE: Our task management tool, Trello, acts as our live agent-task view across all deliverables

DELIVERABLE 4 (STAGE 2)

	Tasks					TYPE	DUE	Status	Comments
Agents		Vivian	Dennis	Ryan	Moath	Kedar	Anwar	Alice
	CODE
	Add line graph	x			x				Mandatory	Nov 23 2016	IN PROGRESS	in the previous deliverable, kedar, moath and vivian were initally going to work together on the graphs. In the middle of the previous deliverable, it was determined that Moath was okay on his own. For this deliverable Moath continued to work on his own and had Vivian review his code
	allows the user to open, edit and save the records they have edited					x		stretch	Dec 7 2016	IN PROGRESS
	Adding session save state					x		Mandatory	Nov 23 2016	DONE: nov 21
	Add stacked bar graph				x				Mandatory	Nov 23 2016	IN PROGRESS
	ability to sort by a user selected list	x				x			Mandatory	Nov 23 2016	DONE: nov 22	Kedar did not do this task and so Vivian ended up doing it
	implement navigation of erroneous entries when CSV files are loaded for the first time			x		x	x	x	Mandatory	Nov 23 2016	IN PROGRESS	three members were assigned this task, but did not do it. Anwar ended up taking on this task
	ability to sort by member division			x		x	x	x	Mandatory	Nov 23 2016	DONE	note: three members were assigned this task, but alice worked on this. However, her code ended up being scrapped because it was deemed extremely inefficient. Anwar ended up figuring out how to do this whilst working on session save
	error handling of missing mandatory fields			x			x	x	Mandatory	Nov 23 2016	DONE
	fix the crashing issue when loading the new sample data					x		x	Mandatory	Dec 7 2016	IN PROGRESS
	Add tab closing “x”					x		stretch	Nov 23 2016	DONE
	Output session info to file					x		stretch	Nov 23 2016	DONE
	editable text fields (aple picker mp4)					x		stretch	Nov 23 2016	IN PROGRESS
	allow user to select multiple rows					stretch		not assigned	this feature is similar to how the user selected list works
	change ui to be more aesthetically pleasing	x			x				stretch	Nov 23 2016	IN PROGRESS	was assigned to some members, they have not communicated their progress

	test cases	x	x	x	x	x	x	x	stretch			left open to everyone, but no time to do
	test matrices	x	x	x	x	x	x	x	stretch

	OTHER
	supply a training video		x		x				stretch	Dec 7 2016	IN PROGRESS	was assigned to some members, but it was determined that this would be done in del 5
	verify the code deck for operation on an iOS platform		x					stretch	Dec 7 2016	unassigned	was going to verify for this stage, but due to time constraints, we are considering this task for the next deliverable
	verify the code deck for operation on Windows 7 OR Windows 10	x	x	x			x	x	Mandatory	Nov 23 2016	DONE	members were assigned to help test, but some did not do
	deliver an easy installation wizard	x	x					Mandatory	Nov 23 2016	DONE	NOTE: installation fails on a machine with no QT because a directory was misnamed ("platform" should be "platforms")
	deliver an installation guide (PDF)					Note: this requirement was not specified until the customer session AFTER deliverable 4 was due
	deliver an executable	x					Mandatory	Nov 23 2016	DONE

	DOCUMENTATION
	update use case diagram	x					x	Mandatory	Nov 23 2016	DONE
	update class diagram	x					x		Mandatory	Nov 23 2016	DONE
	sequence diagram	x		x		x			Mandatory	Nov 23 2016	DONE	Note: only one sequence diagram was done at this point because members did not do their task, and it was not specified that there should be more
	package diagram		x					Mandatory	Nov 23 2016	DONE
	doc: design patterns	x	x					Mandatory	Nov 23 2016	DONE: nov 22
	doc: explaining the implemented features (and states if feature is mandatory or stretch)	x	x	x					Mandatory	Nov 23 2016	DONE
	document: implementation in c++	x					Mandatory	Nov 23 2016	DONE

	development plans timeline		x					Mandatory	Nov 23 2016	DONE
	organize agent-view	x					Mandatory	Nov 23 2016	DONE
	Organize task management system (Trello)	x	x		x		x		Optional	Nov 23 2016	DONE
	Plan task allocation from Stage 2 to Stage 3	x	x	x	x	x	x	x	Mandatory	Nov 23 2016	DONE
	Finalize code and merge	x	x				x		Mandatory	Nov 23 2016	DONE
	Organize meeting minutes up to date	x					Mandatory	Nov 23 2016	DONE

DELIVERABLE 5 (Stage 3)

Agents
	Tasks					TYPE	DUE	Status	Comments
		Vivian	Dennis	Ryan	Moath	Kedar	Anwar	Alice
	CODE
	Add line graph				x				Mandatory	Dec 7 2016	done
	Add stacked bar graph				x				Mandatory	Dec 7 2016	done
	allows the user to open, edit and save the records they have edited					x		stretch	Dec 7 2016	done
	update the user selected list to work with expanded/the new data sets	x					Mandatory	Dec 7 2016	DONE: dec 5
	update buttons on USL	x					Mandatory	Dec 7 2016	DONE: dec 5	fixed the "remove index" button and added an "undo last index" button. Fixed enabling/disabling of buttons
	Fix the user selected list crashing	x					Mandatory	Dec 7 2016	DONE: dec 5
	update the user selected list so that it displays the graph for the list	x			x	x			Mandatory	Dec 7 2016	incomplete	this task was assigned to members, but they did not do it. Vivian ended up working with Kedar to write pseudo code and part of the code for the feature (commented out). These are provided in the document and the code itself
	fix the crashing issue when loading the new sample data					x	x	x	Mandatory	Dec 7 2016	DONE: dec 5	some members did not finish this task. anwar ended up doing it on his own
	implement navigation of erroneous entries when CSV files are loaded for the first time					x		Mandatory	Dec 7 2016	DONE: dec 2
	change ui to be more aesthetically pleasing	x	x	x	x				stretch	Dec 7 2016
	User experience enhancements: add day/night theme changer		x					stretch	Dec 7 2016	DONE: dec 5
	User experience enhancements: add a splash screen	x	x	x					stretch	Dec 7 2016	DONE: dec 5

	test cases	x	x	x	x	x	x	x	stretch	Dec 7 2016		no time
	test matrices	x	x	x	x	x	x	x	stretch	Dec 7 2016

	OTHER
	verify the code deck for operation on an iOS platform					stretch	Dec 7 2016
	verify the code deck for operation on Windows 7 OR Windows 10	x	x				x		Mandatory	Dec 7 2016	done
	supply a training video					stretch	Dec 7 2016	done
	deliver a user guide (PDF)			x					Mandatory		done
	deliver an installation guide (PDF)			x					Mandatory	Dec 7 2016	done
	deliver an easy installation wizard	x					Mandatory	Dec 7 2016	done
	deliver an executable	x					Mandatory	Dec 7 2016	done

	DOCUMENTATION
	update class diagram	x					x		Mandatory	Dec 7 2016	done
	update use case diagram	x					Mandatory	Dec 7 2016	done
	update sequence diagrams (at least 4)	x					Mandatory	Dec 7 2016	done
	update package diagram		x					Mandatory	Dec 7 2016	done

	final doc: title page, table of contents	x	x					Mandatory	Dec 7 2016	done
	final doc: code inspection	x				x			Mandatory	Dec 7 2016	done
	final doc: implementation in C++	x	x					Mandatory	Dec 7 2016	done
	final doc: description of requirements implemented	x	x					Mandatory	Dec 7 2016	done
	final doc: design patterns	x					Mandatory	Dec 7 2016	done
	final doc: lessons learnt	x	x	x	x	x	x	x	Mandatory	Dec 7 2016	done

	development plans: agent task view (ACTUAL)	x					Mandatory	Dec 7 2016	done
	development plans: agent task view (PLANNED)	x					Mandatory	Dec 7 2016	done
	development plans: timeline		x					Mandatory	Dec 7 2016	done

	Organize task management system (Trello)	x	x	x	x		x		Optional	Dec 7 2016	done
	Organize meeting minutes up to date	x					Mandatory	Dec 7 2016	done
	Finalize code and merge	x	x				x		Mandatory	Dec 7 2016	done